## 15th October to 20th October
DATE | PARTICULARS | DEPARTMENT | NEW SCREEN /EXISTING SCREEN CHANGE (Please write the name of the screen) | DATABASE CHANGES IF YES THEN IN WHICH TABLE | Status
2012-10-22 |  | Dispatch | Added "Upload Document" functionality in the page / Changed order of fields | Yes / Table Name : InwardRegister | Done
|  | Common | New page has been added to application named Worksheet Register for managing details of inward | Yes / Table Name : WorkSheetRegister | Done
|  | Common | New page has been added to application named File Register for managing file details of each letter | Yes / Table Name : File | Done
|  | Dispatch | New Page has been added to application named Outward Register with new formats - Added officeMaster / Office types in the database | Yes / Table Name : OutwardRegister / OfficeTypes / Offices | Done
|  | Common | New page has been added to application named Govt Docs Register - Insert / Update completed | Yes / Table Name : GovtDocs | Done
|  | Common | New page has been added to application named SO File Register - Insert / Update completed | Yes / Table Name : SOFile | Done
|  | Common | New page has been added to application named MLA / Minister Regsiter- Insert / Update completed | Yes / Table Name : MLA | Done
|  | Common | New page has been added to application named Vidhansabha Tarankit register- Insert / Update completed | Yes / Table Name : VidhansabhaRegister | Done
|  | Common | New page has been added to application named RTI Appeal egister - insert / Update completed | Yes / Table Name : RTI | In Progress
|  | Common | New page has been added to application named High Court Register- Insert/Update completed | Yes / Table Name : HighCourtReg | In Progress
|  | Common | New page has been added to application named PIO & APIO Register- Insert/Update completed | Yes / Table Name : PIO | In Progress
|  | Common | New page has been added to application named Vigilance Register- Insert/Update completed | Yes / Table Name : Vigilance | In Progress